NAGARJUNA COLLEGE OF INFORMATION TECHNOLOGY

Shankhamul-9, Lalitpur

SET A

Mid-Term Exam-2082

Bachelor Level /Fourth Year/ Seventh Semester/ Science				Full Marks: 40

B.Sc. CSIT  (CSC 415)									Pass Marks: 16

(Software Project Management) 								Time: 2 Hrs.

Candidates are required to give their answer in their own words as far as practicable. The figures in the margin indicate full marks.

Group A

Long Answer Questions.

Attempt any ONE questions.									[1×10=10]

- Explain about feasibility study – plan – execute cycle with suitable diagram. A project with a 4-year life and a cost of Rs. 100,000 in the beginning, generates revenue of Rs. 25,000 every year, also it will generate Rs. 65,000 in year 3. If the discount rate is 8%, what is the Annual worth of the project? [4+6]

- What is program management? What is its role on project lifecycle? Explain stages in contract placement. Categorize software projects. [2+1+3+4]

Group B

Short Answer Questions.

Attempt any SIX questions.										[6×5=30]

- What is Work Breakdown Structure(WBS), explain with suitable example. Explain product and activities in the projects.  [3+2]

- How do you define software project management? How it contrast from other project? [2+3]

- What is project evaluation? Why it is done? By which level of management it is generally done?  [1+3+1]

- Compare technical assessment with economic assessment. [5]

- What is NPV  analysis? How cash flow forecasting eradicates NPV analysis problems explain with relevant example. [2+2+1]

- Define risk in the SPM. Explain in brief, risk framework.  [1+4]

- A project has the following activities with their durations and dependencies:

| Activity | Duration (days) | Predecessor(s) |
| --- | --- | --- |
| A | 3 | - |
| B | 2 | A |
| C | 4 | A |
| D | 2 | B, C |
| E | 3 | D |

- Draw the project network diagram.

- Calculate the Earliest Start (ES), Earliest Finish (EF), Latest Start (LS), and Latest Finish (LF) for each activity.

- Identify the critical path and the project duration. [2+2+1]

●●●

NAGARJUNA COLLEGE OF INFORMATION TECHNOLOGY

Shankhamul-9, Lalitpur

SET B

Mid-Term Exam-2082

Bachelor Level /Fourth Year/ Seventh Semester/ Science				Full Marks: 40

B.Sc. CSIT  (CSC 415)									Pass Marks: 16

(Software Project Management) 								Time: 2 Hrs.

Candidates are required to give their answer in their own words as far as practicable. The figures in the margin indicate full marks.

Group A

Long Answer Questions.

Attempt any ONE questions.									[1×10=10]

- How the Lyynen–Mathiassen–Ropponen risk framework helps to categorize the risks. Explain in brief, the framework for dealing with risk. [3+7]

- What is strategic assessment? Explain the role of organization goal while doing strategic assessment. Why technical assessment is necessary for the software project explain with example. [2+3+5]

Group B

Short Answer Questions.

Attempt any SIX questions.										[6×5=30]

- Explain Software Product and its general types. How the software project management is different from other project management [2+3]

- What is scheduling? What are the steps for scheduling? [2+3]

- What is the role of planning in SPM? Why detailed planning is not done at the beginning, explain with example. [2+3]

- Compare technical assessment with strategic assessment. [5]

- What is NFV  analysis? How cash flow forecasting eradicates NFV analysis problems explain with relevant example. [2+2+1]

- Explain the significance of tolerance line. When to use Checklist and brainstorming methiods  [2+3]

- A project has the following activities with their durations and dependencies:

| Activity | Duration (days) | Predecessor(s) |
| --- | --- | --- |
| P | 4 | - |
| Q | 3 | P |
| R | 5 | P |
| S | 2 | Q, R |
| T | 4 | S |

- Draw the project network diagram.

- Calculate the Earliest Start (ES), Earliest Finish (EF), Latest Start (LS), and Latest Finish (LF) for each activity.

- Identify the critical path and the project duration.	 [2+2+1]

●●●